## Sheet1
Task (ranked by priority) | Duration | Note
Create second thread for handling serial communication. | 4 days | Look into communication between the serial thread and gui thread. Possible options ar portected buffers/variables r or futures.
General clean-up of Qt GUI. | 1 day
Re-think layout (especially plots). | 2 days | Ongoing
Test | 3 days | Ongoing - will carry over for the end of October deadline where testing will be more stringent
Note for Nick: Ensure that you can program/debug MCU - not high priority